## Architecture
Tasks | Status | Comments | Owner
Project Architecture
Micro Service Architecture | Done | REST service for handing database interaction | Gaurav
SSR / API Gateway Architecture | In Progress | Handling SEO, Gateway layer, Page sharing etc. | Gaurav | Currently working on minor fix for warning
Database Design | Done | Done for cinema specific features, pending for user management | Gaurav
Admin Section | Done | For adding movies/theater/dates. The values are dynamically generated based on logic for less effort in data entry | Gaurav
Documentation | In Progress | As in when required | Gaurav

## Microservice
Tasks | Status | Owner
APIs
Get All Movie | Done | Gaurav
Get All Theatres | Done | Gaurav
Get Movies - based on theatre | Done | Gaurav
Search Movies - based on theatre | Done | Gaurav
Get Movies - based on theate and based on date (mm/dd/yyyy) | Done | Gaurav
Get Movies - based on theatre/date/timeStart/timeEnd | Done | Gaurav
Get Dates/Movie Details - based on theatre | Done | Gaurav
Seat selection | Pending
User management | Pending
Booking management | Pending

## Functionalities
Tasks | Status | Comments | Owner
Functionalities
Choose Theatre | Done | Listing all theater in start | Harendra
Show screening movies based on theater | Done | Show all movies based on theater selected | Harendra
Search movies | Pending | Search movies from list
Choose Movie | Pending | Select movies and show attributes
Choose timing | Pending | Time selection functionality for filtering movies
Choose seats | Pending | Show seat map and select seat functionality
Book Movie | Pending | Book seat for the user and update available seat for that event.
Tabbing functionality | Pending | For both flow

## Component + Styling + Unit Test
Tasks | Status | Comments | Owner
Styling and component creation
Theater Page | Pending
Movie List Page | Pending
Search Box | Pending
Time selection Component | Pending
Movie Page with time selection functionality | Pending
Seat selection page | Pending
Booking Confirmation page | Pending
Tabbing and movie selection | Pending
Unit Test cases Zest enzyme | Pending | For Component/ Pages/ Containers only | Satyendra